## Team Composition
Team Name: | team one |  | Product Domain/Industry: |  | Project time-line
Takeout
Member Name |  | Primary Responsibility |  |  | Start Date | End Date
Product Description:
|  | Coordinator/Lead |  | Food takeout service | 2022-10-03 | 2022-11-30

## Dashboard
Copyright - Sudharsan Iyengar - August 2017.
Tracking Project Work
| Team Name: | Team One |  |  |  | Member Contribution |  | Component Effort
Project Description:
| Activity | Time Spent | # of revisits to this activity | Output Artifact (formal and informal) | % of work done by due date | Team Member Name | Total time Spent | Component Name | Total time spent on component
Understanding the problem
Creating a model for the solution
Writing the Code using an IDE (initial)
Testing the code - number of runs
Feedback from testing and completion
Team Meetings:

## Product Schedule
| To Do List: |  |  | Review and Notes/Reflections
Date to start
2022-10-03 | Initial List: |  | Define Team Members | Dawson, Praise, Kevin, Nick, Martin, Sheikh
|  |  | Decide on Team Name | Team One
|  |  | Define Member Roles | Dawson, Kevin Front end
|  |  | Identify Product Domain | Resturaunt / Takeout
|  |  | Develop Product Description | Product is a takeout app developed for restaurants. Undecided customers can browse food menus and decide on which food items to purchase. Decided customers can then submit their order to the kitchen for cooking.
2022-10-10 | Items Added | Plan Sprint I | Review/refine Product Description | The ability for undecided customers to see store hours. Managers can set store hours. Managers can close order acceptance.
|  |  | Develop and set team schedule | Meet on Tuesdays or Thursdays at 2:30pm
|  |  | Develop Product Goals | Allow customers to order food. Allow manager to update the menu to provide information relative to the menu's items(prices). Allow cooks and managers to login. Allow cooks to update ingredients and confirm food orders.
|  |  | Evaluate Feasibility and Risks | Someone could prank restraunt and purchase food. Then not pick up their food and not pay. Spamming. Legality.
|  |  | Review/refine Product Goals | Should be able to run on everything
Describe Product for Engineering - V & S document
Review Feature List and prioritize
Allocate tasks for Sprint I
Create Initial Gantt Chart
2022-10-17 | Interim review - Sprint I | Design | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-19 | Interim review - Sprint I | Implement and Test | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-24 | Interim review - Sprint I | Implement and Test | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-26 | Sprint I Complete and Presented | Deploy and Plan Sprint II | Present your project progress and outcomes to class; reflections
2022-10-28 | Start Sprint II |  | Review and Prioritize Features
Allocate tasks for Sprint II
Create Initial Gantt Chart
2022-11-02 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-07 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-14 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-16 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
11/28-11/30 | Sprint II Complete and Presented | (Exam 2 - 12/2) | Present your project progress and outcomes to class; reflections

## Product Backlog
Unique UC Log ID | Short User Story | Created by and Date | Reference - what prompted | Relevant Component | Estimate (Hrs.) | Priority | Status
Ex: 5 | Ex: Authorized user wants to view an item | Ex: John, 3/15/19 | Ex: Customer Request | (Ex: UI, Security, DBAccess, ..) | 4 Hrs. | Ex: High, Medium, Low | Ex: Completed, Assigned (Spring #), Backlog
86 | Post-order customer wants to track delivery | 2022-11-17 | Team brainstorm | CartUI, DB | 2 hrs. | Medium | Unassigned | Password Management
22 | Customers want to login using the API of another service they use (login with Meta, Apple, etc.) | 2022-11-17 | Team brainstorm | LoginUI, DBObject | <1 hr. | Low | Unassigned
25 | Customers want to login using FaceID | 2022-11-18 | Team brainstorm | LoginUI, DBObject, Controllers | 6 hrs. | Low | Unassigned
68 | Staff wants a revamp of menu customization | 2022-11-18 | Team brainstorm | Employee UIs (manager role), DBObject | 5 hrs. | Medium | Unassigned
3 | Customers would like to use Apple pay and other convenient payment services to order food | 2022-11-18 | Team brainstorm | CartUI, DB, controllers | 2 hrs. | Medium | Unassigned
90 | Managers should be able to remove former employees from the system | 2022-11-28 | Team brainstorm | A new ManagerUI | 2 hrs. | High | Unassigned

## Understanding the Problem
Understanding the Problem
Date | Component | Member Name | Time spent in minutes | Brief description of output
2022-10-04 | Vision and Scope | Team Meeting | 63 | Start to vision and scope
2022-10-06 | Vision and Scope | Team Meeting | 90 | Finishing vision and scope
2022-10-11 | Use Cases | Team Meeting | 54 | A concensus on what to focus on
2022-10-13 | Use Case Tables | Team Meeting | 77 | UC diagram on board, UC tables
2022-10-18 | Login Components | Team Meeting | 44 | Understanding of how to make login process function
2022-10-20 | Login Function | Team Meeting | 45 | Finishing login, dummy credentials and items
2022-10-24 | Employee table and menu | Team Meeting | 55 | New employee table, menu
2022-10-25 | GitHub Repo | Team Meeting/ Dawson and Nicholas | 94 | Codebase genesis, creating branches, verifying git works on machines, merging code
2022-11-01 | Trying to figure out what to accomplish in Sprint 2 | Team | 38 | Refining goals for sprint 2
2022-11-03 | Ordering our priorities for Sprint 2 | Team Meeting | 85 | A list of Use Cases + Features that the team determined would be of the highest priority and value to the user
2022-11-08 | Discussing a proper customer UI | Team Meeting | 81 | Rough blueprint for customer UI, delegated to team member martin
2022-11-10 | Discussing backend controllers rework | Team Meeting | 73 | Properly diagrammed models of the control structure behind the project
2022-11-15 | Discussing session logging process (employee timeout) | Team Meeting | 31 | Cohesive idea about how session logging should work
2022-11-17 | Finalizing customer page layout | Team Meeting | 65 | A clear, concise customer page layout and refining website goals
2022-11-26 | Finishing cart system analysis | Team Meeting | 71 | Finalizing cart, ordering process in the system
2022-11-28 | Evaluating Project Progress | Team Meeting | 117 | Common understanding of where the project stands
2022-11-29 | Merging final code together and testing for presentation | Team Meeting | 92 | Merged final code together, final tests complete

## Component Description
General Description of Components
Name of Component | Brief description of the Component | Team Members responsible
landing page | Landing page for user to access and use to go to login page | Kevin Robles
Login page | Page to login and register | Kevin, Martin, Sheikh
Menu page | Page to view menu items | Kevin
Session handling | Times out inactive users and manages logged in ones | Nick
Database object | Handles persistent data storage | Nick
View Menu Controller | Passes menu items from back end to front end | Praise
Login/Create Account Controller | Handles login process | Nick
"Add to cart" controller | Handles cart state | Nick/Praise
Food item queue | handles food item queue | Nick/Praise
Cart page | displays the cart | Kevin
Order queue page | displays the order queue | Kevin
Customer Menu | Shows menu for customers | Martin
Customer Login | Allows customers to login | Martin
Customer Landing Page | Landing page for customers | Martin
Customer Search Page | Searching functionality for customers | Martin
Customer Profile Page | Customer user profile | Martin
Customer Cart Page | Customer cart page | Martin

## Creating the Model
Creating the Model/UML diagram
Date | Component | Member Name | Time spent in minutes | Brief description of output | *Unless otherwise specified, all diagrammed ouputs were made on platform DRAWIO
2022-10-13 | UC Diagram | Dawson | 5 | drawing on board
2022-10-13 | Sys Seq | Dawson | 43 | Orig SysSeq
2022-10-14 | Class Diagram | Dawson | 35 | Orig Classes
2022-10-13 | UC Table | Team | 74 (agg.) | Updated UC Table
2022-11-11 | UC Diagram | Dawson | 55 | Updated UC
2022-11-20 | Sys Seq | Dawson | 89 | Updated SysSeq
2022-11-20 | Class Diagram | Dawson | 47 | Updated Classes
2022-11-29 | Seq Diagram UC | Dawson | 53 | Updated Seq diagram

## Writing Code
Writing code
Date | Component | Member Name | Time spent in minutes | Brief description of output | No other work time given to documenter
2022-10-10 | setting up database | Nick Moen | 30 minutes | Because the database I already had set up for our previous project, it did not take long to get it setup for this project.
2022-10-15 | create account controller | Nick Moen | 3 hour | Sets up account creation in the database
2022-10-15 | login controller | Nick Moen | 1 hour | Validates user credintials
2022-10-16 | fetch menu from database and display on interface | Nick Moen | 2 hours | Display food menu on interface(I did not write the backend controller)
2022-11-12 | Session class on employee | Nick Moen | 4 hours | Keep track of user sessions
2022-11-18 | create account/login controller for customers | Nick Moen | 2 hours | customer create account and login
2022-11-18 | session class on customer | Nick Moen | 2 hours | Keep track of user sessions for customer application
2022-11-28 | Sessions | Nick Moen | 5 hours | Keeping track of user windows and using session variables
2022-11-29 | Customer order controller | Nick Moen | 20 minutes | I only programmed the remove order part and fixed some code that Praise wrote
2022-11-29 | Frontend order object | Nick Moen | 3 hours | Made the data structure in the frontend that stores the order. Also structured the tables in javascript that display the table to user.

## Testing the code - # of runs
Testing the code - # runs per session
Date | Component | Member Name | Time spent in minutes | Brief description of output | Testing data not given to documenter

## Revisions based on Testing
Revisions based on Testing
Date | Component | Member Name | Time spent in minutes | Brief description of output | Nick revised sesh 11/28/2022
I'm sure others have revised based on testing as well, but communication hasn't been clear on that