## Team Composition
Team Name: | team one |  | Product Domain/Industry: |  | Project time-line
Takeout
Member Name |  | Primary Responsibility |  |  | Start Date | End Date
Product Description:
|  | Coordinator/Lead |  | Food takeout service | 2022-10-03 | 2022-11-30

## Dashboard
Copyright - Sudharsan Iyengar - August 2017.
Tracking Project Work
| Team Name: | Team One |  |  |  | Member Contribution |  | Component Effort
Project Description:
| Activity | Time Spent | # of revisits to this activity | Output Artifact (formal and informal) | % of work done by due date | Team Member Name | Total time Spent | Component Name | Total time spent on component
Understanding the problem
Creating a model for the solution
Writing the Code using an IDE (initial)
Testing the code - number of runs
Feedback from testing and completion
Team Meetings:

## Product Schedule
| To Do List: |  |  | Review and Notes/Reflections
Date to start
2022-10-03 | Initial List: |  | Define Team Members | Dawson, Praise, Kevin, Nick, Martin, Sheikh
|  |  | Decide on Team Name | Team One
|  |  | Define Member Roles | Dawson, Kevin Front end
|  |  | Identify Product Domain | Resturaunt / Takeout
|  |  | Develop Product Description | Product is a takeout app developed for restaurants. Undecided customers can browse food menus and decide on which food items to purchase. Decided customers can then submit their order to the kitchen for cooking.
2022-10-10 | Items Added | Plan Sprint I | Review/refine Product Description | The ability for undecided customers to see store hours. Managers can set store hours. Managers can close order acceptance.
|  |  | Develop and set team schedule | Meet on Tuesdays or Thursdays at 2:30pm
|  |  | Develop Product Goals | Allow customers to order food. Allow manager to update the menu to provide information relative to the menu's items(prices). Allow cooks and managers to login. Allow cooks to update ingredients and confirm food orders.
|  |  | Evaluate Feasibility and Risks | Someone could prank restraunt and purchase food. Then not pick up their food and not pay. Spamming. Legality.
|  |  | Review/refine Product Goals | Should be able to run on everything
Describe Product for Engineering - V & S document
Review Feature List and prioritize
Allocate tasks for Sprint I
Create Initial Gantt Chart
2022-10-17 | Interim review - Sprint I | Design | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-19 | Interim review - Sprint I | Implement and Test | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-24 | Interim review - Sprint I | Implement and Test | Member Feedback on assigned tasks
Update Gantt Chart
2022-10-26 | Sprint I Complete and Presented | Deploy and Plan Sprint II | Present your project progress and outcomes to class; reflections
2022-10-28 | Start Sprint II |  | Review and Prioritize Features
Allocate tasks for Sprint II
Create Initial Gantt Chart
2022-11-02 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-07 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-14 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2022-11-16 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
11/28-11/30 | Sprint II Complete and Presented | (Exam 2 - 12/2) | Present your project progress and outcomes to class; reflections

## Product Backlog
Unique UC Log ID | Short User Story | Created by and Date | Reference - what prompted | Relevant Component | Estimate (Hrs.) | Priority | Status
Ex: 5 | Ex: Authorized user wants to view an item | Ex: John, 3/15/19 | Ex: Customer Request | (Ex: UI, Security, DBAccess, ..) | 4 Hrs. | Ex: High, Medium, Low | Ex: Completed, Assigned (Spring #), Backlog

## Understanding the Problem
Understanding the Problem
Date | Component | Member Name | Time spent in minutes | Brief description of output
2022-10-06 | Understanding the problem |  | 90

## Component Description
General Description of Components
Name of Component | Brief description of the Component | Team Members responsible

## Creating the Model
Creating the Model/UML diagram
Date | Component | Member Name | Time spent in minutes | Brief description of output

## Writing Code
Writing code
Date | Component | Member Name | Time spent in minutes | Brief description of output

## Testing the code - # of runs
Testing the code - # runs per session
Date | Component | Member Name | Time spent in minutes | Brief description of output

## Revisions based on Testing
Revisions based on Testing
Date | Component | Member Name | Time spent in minutes | Brief description of output